## Slide 1
2017 Risk Appetite Statement
Annual Setting
February 2017

## Slide 2
Metrics | Task | January | February | March | April | May | June | July | August
All Metrics | Receive Group Metrics (December) |  |  |  |  |  |  |  | 
All Metrics | Review applicable, full define metrics | SHUSA RA |  |  |  |  |  |  | 
All Metrics | SHUSA Send to Entities | SHUSA RA |  |  |  |  |  |  | 
All Metrics | Identify applicable metrics |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  |  |  | 
All Metrics | Draft qualitative statements |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  |  |  | 
Non-CCAR Metrics | Quantify New and Revised Limits |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  |  |  | 
Non-CCAR Metrics | Co mplete Draft |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  |  |  | 
Non-CCAR Metrics | 1st line, 2nd line and ERM (local and SHUSA) signoff on 1st draft |  |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  |  | 
CCAR Metrics | Quantify New and Revised Limits |  |  | 1st line, 2nd line, Rec/Res and ERM | 1st line, 2nd line, Rec/Res and ERM |  |  |  | 
CCAR Metrics | Co mplete Draft |  |  |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  | 
CCAR Metrics | 1st line, 2nd line and ERM (local and SHUSA) signoff on 1st draft |  |  |  | 1st line, 2nd line, Rec/Res and ERM |  |  |  | 
All Metrics | Review full (CCAR & Non-CCAR) with CRO, COO/ CORO, CFO |  |  |  | ERM, CRO, COO/ CORO, CFO |  |  |  | 
All Metrics | Revise and produce 2nd draft |  |  |  |  | 1st line, 2nd line, Rec/Res and ERM |  |  | 
All Metrics | 1st line, 2nd line and ERM (local and SHUSA) signoff on 2nd draft |  |  |  |  | 1st line, 2nd line, Rec/Res and ERM |  |  | 
All Metrics | Review with CRO, COO/ CORO, CFO & CEO |  |  |  |  | ERM, CRO, COO/ CORO, CFO & CEO |  |  | 
All Metrics | Entity CRO, CFO & CEO signoff on finalized draft |  |  |  |  | ERM, CRO, CFO & CEO |  |  | 
All Metrics | Review with SHUSA CRO, COO/ CORO & CFO |  |  |  |  | Entity & SHUSA ERM, CRO, COO/ CORO, & CFO |  |  | 
All Metrics | Revise and produce 3nd draft |  |  |  |  | Entity & SHUSA 1st line, 2nd line, ERM |  |  | 
All Metrics | 1st line, 2nd line and ERM (local and SHUSA) signoff on 3st draft |  |  |  |  | Entity & SHUSA 1st line, 2nd line, ERM |  |  | 
All Metrics | Review with Entity & SHUSA CRO, COO/ CORO, CFO & CEO |  |  |  |  | Entity & SHUSA ERM, CRO, COO/ CORO, CFO & CEO |  |  | 
All Metrics | SHUSA & Entity CRO, CFO & CEO signoff on finalized draft |  |  |  |  | Entity & SHUSA ERM, CRO, CFO & CEO |  |  | 
All Metrics | Entity & SHUSA ERC, RC & Board Meetings & Revisions, final signoff |  |  |  |  |  | ALL Hands |  | 
All Metrics | Glossary Update |  |  |  |  |  | Entity & SHUSA ERM | Entity & SHUSA ERM | Entity & SHUSA ERM
A. 2017 Annual Setting Timeline Overview
Identify metrics and draft qualitative statements
Quantify Non-CCAR metrics and sign off on draft
Quantify CCAR metrics and sign off on draft
Review, revise and sign off on all metrics
3
4
1
2
5
Final sign-off on all metrics

## Slide 3
Milestone | Task | Accountable | Proposed Start Date | Due Date | Deliverables | Notes | Status
1. Identify metrics and draft qualitative statements | Receive Group Metrics (December) | Group RA | N/A | 12/2016 |  |  | Completed
 | Review applicable, fully defined metrics | SHUSA RA | N/A | 1/2017 |  |  | Completed
 | SHUSA send to Entities | SHUSA RA | N/A | 2/2/2017 |  |  | Completed
 | Identify applicable metrics & draft qualitative statements | 1st line, 2nd line, Rec/Res and ERM | 2/2/2017 | 2/24/2017 |  | Seek Executive Feedback | 
2. Quantify Non-CCAR metrics and sign off on draft | Quantify New and Revised Non-CCAR Limits – Complete 1st Draft | 1st line, 2nd line, Rec/Res and ERM | 2/2/2017 | 2/24/2017 |  |  | 
 | 1st line, 2nd line and ERM (local and SHUSA) signoff on 1st draft | 1st line, 2nd line, Rec/Res and ERM | 2/25/2017 | 3/24/2017 | Non CCAR linked metrics qualitative statement, quantitative calibration, and supporting documents (1st Draft) | Seek Executive Feedback | 
3. Quantify CCAR metrics and sign off on draft | Quantify New and Revised CCAR Limits – Complete 1st Draft | 1st line, 2nd line, Rec/Res and ERM | 3/6/2017 | 4/28/2017 |  |  | 
 | 1st line, 2nd line and ERM (local and SHUSA) signoff on 1st draft | 1st line, 2nd line, Rec/Res and ERM | 4/14/2017 | 4/28/2017 | CCAR linked metrics qualitative statement, quantitative calibration, and supporting documents (1st Draft) | Seek Executive Feedback | 
4. Review, revise and sign off on all metrics | Review full (CCAR & Non-CCAR) with CRO, COO/ CORO, CFO | ERM, CRO, COO/ CORO, CFO | 4/14/2017 | 4/28/2017 |  |  | 
 | Revise and produce 2nd draft | 1st line, 2nd line, Rec/Res and ERM | 5/1/2017 | 5/26/2017 |  |  | 
 | 1st line, 2nd line and ERM (local and SHUSA) signoff on 2nd draft | 1st line, 2nd line, Rec/Res and ERM | 5/12/2017 | 5/26/2017 |  |  | 
 | Review with CRO, COO/ CORO, CFO & CEO | ERM, CRO, COO/ CORO, CFO & CEO | 5/12/2017 | 5/26/2017 |  | Recommend take to ERMC/ERC for review & feedback | 
 | Entity CRO, CFO & CEO signoff on finalized draft | ERM, CRO, CFO & CEO | 5/12/2017 | 5/26/2017 |  |  | 
 | Review with SHUSA CRO, COO/ CORO & CFO | Entity & SHUSA ERM, CRO, COO/ CORO, & CFO | 5/12/2017 | 5/26/2017 |  |  | 
 | Revise and produce 3rd draft if needed | Entity & SHUSA 1st line, 2nd line, ERM | 5/12/2017 | 5/26/2017 |  |  | 
 | 1st line, 2nd line and ERM (local and SHUSA) signoff on 3st draft | Entity & SHUSA 1st line, 2nd line, ERM | 5/12/2017 | 5/26/2017 | All metrics qualitative statement and quantitative calibration, RAS Framework, MRE and supporting documents (revised version) |  | 
5. Final sign-off on all metrics | Review with Entity & SHUSA CRO, COO/ CORO, CFO & CEO | Entity & SHUSA ERM, CRO, COO/ CORO, CFO & CEO | 5/26/2017 | 6/9/2017 |  |  | 
 | SHUSA & Entity CRO, CFO & CEO signoff on finalized draft | Entity & SHUSA ERM, CRO, CFO & CEO | 5/26/2017 | 6/9/2017 | All metrics qualitative statement and quantitative calibration, RAS Framework, MRE and supporting documents (final version) |  | 
 | Entity & SHUSA ERC, RC & Board Meetings & Revisions, final signoff | ALL Hands | 6/9/2017 | 6/30/2017 SIS, SSLLC,SAM,SFS TBD |  | ERMC, ERC, RC, Board Entity and SHUSA for Approval | 
All Metrics | Glossary Update | Entity & SHUSA ERM | 6/30/2017 | 9/1/2017 |  |  | 
B. Activity, Deliverable and Deadline
All due dates are to be treated as the absolute last date. If you have committee or board meetings occurring prior to those dates, then move up your due dates to meet local deadlines. Note these deadlines cannot be moved out, just up.

## Slide 4
C. Stakeholder Roles and Responsibilities
1LOD
2LOD
ERM
Ultimate responsibility for creating and calibrating RAS metrics and limits
Assess current and new metrics and limits. Evaluate against all applicable material: historical views, projected/forecasted, industry best practice, regulatory guidance, strategic plans and CCAR/stress tests
Develop proposal for metric inclusion and limits. Provide supporting documentation
Provide guidance to 1LOD for development of RAS metrics and limits
Serve as source of expert judgment for appropriate entity risk type for development of metrics and limits. Ensure appropriate coverage of applicable risks. Evaluate metrics and limits proposed by the 1st line
Guide and oversee entire RAS effort for respective entity (SHUSA ERM to coordinate efforts across all IHC entities), ensure smooth flow of communication
Provide review and challenge of any proposed metrics and limits, and linking procedures
Ensure RAS tasks are completed on time to adhere to specified completion dates
Ensure first line and second line teams are fully integrated in revising the RAS.
Submit the entity proposed RAS to the SHUSA RAS team for review
Ensure all 1st line, 2nd line, entity executive and SHUSA executive signoffs are obtained
Update RAS Framework; RAS Glossary; and Monitoring, Reporting and Escalation procedures
Ensure RAS supporting documentation is complete

## Slide 5
D. Potential 2017 New Metrics - Additional Metrics in 2016 RAS (1/6)
Type | Metrics | Group Definition | In Group RAS?
P&L volatility | Cost of Credit | Measures the creditworthiness of the portfolio, and permits traceability with the strategic plan and budget, risk policies and indicators on the contingency plan. It expresses the net credit provisions incurred by the Group during the year (last 12 months) in terms of percentages of the average loan portfolio. | Y
P&L volatility | Net NPL entries | Measures the credit quality of the portfolio through the volume of net NPL (Non-performing loans) entries over the average credit exposure of the portfolio. | Y
P&L volatility | NPL Coverage Ratio | Measures the level of coverage of the non-performing loans in terms of Reserves (provision stock). | Y
Solvency | Maximum projected deterioration of CET1 ratio | Controls significant deviations between the stressed and baselines case, in the CET1 ratio (or the corresponding ratio if the country is not subject to Basel III regulations) on the business plans and capital planning over 3 years. | Y
Solvency | Impact on CET1 of the simultaneous default of the 5 main wholesale counterparties (Jump to Default Top 5 over CET1) | Impact on the CET1 ratio of an unexpected event of simultaneous default of the 5 main corporate counterparties, considering a LGD of 45%, and expressed in basis points | Y
Solvency | Minimum projected CET1 (fully-loaded) in normal conditions | Expresses a minimum value of the Common Equity Tier 1 Ratio, under fully-loaded criteria (measured in terms of Basel III), which the Group wishes to maintain in normal conditions during a time horizon of 3 years. | Y
AML | Customers with “high risk” profile (Percentage of high risk customers) | It is expressed as a percentage. It is the quotient between the number of customers classified as “high risk” (based on internal policies) and the total number of customers. | Y
When adding a primary RAS metric, please consider whether the metric is material enough to merit inclusion, whether the metric has real business implications, whether the metric applies to your entity and whether data availability and quality allows to include.
ERM team is expected to work with 2LOD (provide guidance) and 1LOD (provide assessment) where necessary.

## Slide 6
Type | Metrics | Group Definition | In Group RAS?
Non-financial risks – Fraud | Card fraud rate (Credit / Debit) | Measurements are in number of cases, which refer to the number of cases of debit and credit card fraud for each 10,000 active cards over a one-month time frame. | Y
Non-financial risks – Fraud | Online banking fraud rate | Measurements are in number of cases, which refer to the number of cases of on-line banking fraud for each 10,000 users over a one-month time frame. | Y
Non-financial risks – Tech | IT relevant incidents | It is expressed as quantity. The number of P1 and P2 incidents are measured over a one-month time frame. | Y
Non-financial risks – Tech | IT system availability | It measures the availability of critical systems during the month: time that the systems have no failure that affects their availability. | Y
Non-financial risks – Tech | Servers with obsolete operating systems | It is expressed as a percentage. The number of servers with obsolete operating systems / the total number of servers. | Y
Non-financial risks – Cyber | Secure operating systems | It is expressed as a percentage. The number of operating systems that are not compliant with the security policy / the total number of logical servers. | Y
Non-financial risks – Cyber | Ethical hacking vulnerabilities | It is expressed as quantity. Number of high-risk vulnerabilities detected in tests conducted by the Ethical Hacking service that have not been corrected for more than three months. | Y
D. Potential 2017 New Metrics - Additional Metrics in 2016 RAS (2/6)

## Slide 7
Type | Metrics | Local Definition | In Group RAS?
Capital adequacy | Loss impact on trading portfolio | Impact of stress in trading portfolio assuming 1 month under stress (since 2007 only higher losses are taken once every 60 months, 1 month every 5 years) and poor performance over the remaining 11 months. The trading activity represents the SBNA client facilitation portfolio. | N
Capital adequacy | GCB Concentration Risk | Concentration losses arising from a probability of 1 in 40 years economic scenario | N
Credit risk (concentration) | Top 20 Financial Institutions exposure | The sum of the value of total exposure to any individual customer (or aggregated to guarantor) of a Financial Institution (excludes mortgage clearing houses) relative to equity, defined as CET1 plus ACL | N
Credit risk (concentration) | Large exposures | Exposure > 2% of SHUSA shareholders equity | N
AML | Number of OFAC blocks and violations | Number of OFAC events requiring immediate attention to ensure OFAC Compliance | N
AML | Percentage of pending KYC updates overdue (>90 days) | Percent of total clients pending for Know Your Customer (KYC) updates | N
AML | Average percentage of AML transaction monitoring alerts awaiting disposition (>30 days) Number of AML transaction monitoring alerts awaiting disposition (>60 days) (BSI) | Pending AML alerts awaiting clarification for more than 30 days | N
D. Potential 2017 New Metrics - Additional Metrics in 2016 RAS (3/6)

## Slide 8
Type | Metrics | Group Definition
P&L volatility | Return On Tangible Equity (ROTE) | Profit attributable to the Group (Annualized) over tangible Equity. This takes into account the following lines: Shareholders' Equity, Valuation Adjustments, Yearly Profit, Intangible Goodwill and Assets w/o Goodwill.
Liquidity | Liquidity horizons in stress (idiosyncratic crisis) | It measures, in number of days, the liquidity available in the event of different liquidity crisis scenarios (local systemic, global systemic, idiosyncratic and wholesale crisis).
AML | Customers with no risk profile | It is expressed as a percentage. It is the quotient between the number of customers with no risk profile and the total number of customers.
AML | AML related sanctions | It is expressed as absolute value. Number of penalties/fines that the unit has received on a quarterly basis due to non-compliance of AML or with the international financial restrictions regime (sanctions).
Compliance | % Employees with Code of Conduct in Securities Market (CCSM) signed | It is expressed as a percentage. It is the quotient between the number of employees that have signed the CCSM and the total number of employees subjected to CCSM.
Compliance | % Employees with Code of Conduct in Securities Market (CCSM) training completed | It is expressed as a percentage. It is the quotient between the number of employees that have performed the CCSM compulsory training and the total number of employees subjected to CCSM.
Compliance | % of staff with General Code of Conduct (GCC) training completed | It is expressed as a percentage. It is the quotient between the number of employees that have performed the GCC compulsory training and the total number of employees subjected to GCC.
D. Potential 2017 New Metrics - Group Metrics beyond 2016 RAS (4/6)

## Slide 9
Type | Metrics | Group Definition
Products gov. & Customer protection | Investment portfolio profile (products with rating #5) | It is the quotient between the market value of those products classified as risk #5 risk (based on internal policies) and the total number of products.
Products gov. & Customer protection | Products under special monitoring | This metric measures the number of products that, due to a flaw on its design, commercialisation process or trends have generated losses or non expected unfavourable results or just because the entity has decide to apply a special monitoring.
Products gov. & Customer protection | Customer complaints considering favorability | The indicator is a combination of 2 metrics: -complaints volume, over 10,000 customers: Number of complaints for which resolutions have been issued -% of complaints in favour the customers: Percentage of complaints for which resolutions in favor to the client have been issued
Non financial & Cross risk | Maximum Risk Profile (RI&A scoring) | The risk profile score is the representation at a given point in time of the organization's overall exposure to key risks, both under current and potential stressed conditions through the combination of risk performance, control environment and sensitivity analysis.
Non financial & Cross risk | Internal Audit recommendations (requiring immediate attention) past-due | It considers the number of Internal Audit recommendations classified as “requiring immediate attention” (or “RIA”), for which the planned implementation date has been past-due for more than three months
Non financial & Cross risk | Loss Multiplier | Based on new the Loss Component of Basel´s Standardized Measurement Approach (SMA).
D. Potential 2017 New Metrics - Group Metrics beyond 2016 RAS (5/6)

## Slide 10
Type | Metrics | Group Definition
Non-financial risks – Model Risk | Percentage of highly material models without significant flaws | It measures the number of models in Santander Group without any identified substantial weaknesses, over the total number of models classified as having “high importance”. It is expressed as a percentage.
Non-financial risks – Model Risk | Percentage of models with highly relevant recommendations | It is measured as the number of models with recommendations of high importance that have not yet been implemented, over the total number of models.
Non-financial risks – Model Risk | % Coverage IRB Models | Measures the percentage of current exposure (measured in EAD terms) which is covered by IRB models approved by the regulator. Calculated as EAD covered by IRB models approved by the regulator / Total EAD
D. Potential 2017 New Metrics - Group Metrics beyond 2016 RAS (6/6)

## Slide 11
Appendix

## Slide 12
E. Reference Materials for 2017 Annual Setting
Non-CCAR linked metrics: “2016 RAS non-CCAR linked metrics” Excel document for SBNA, SC, BSPR, BSI, SIS and SSLLC
CCAR linked metrics: RAS mini tool for SBNA, SC, BSPR
2016 Entity RAS Board Deck
2016 Entity RAS Supporting Materials
2016 Entity Risk Appetite Statement, Framework and MRE

## Slide 13
Entity | ERMC/ERC | RC | Board
SHUSA | 6/7/2017 | 6/14/2017 | 6/15/2017
SBNA | ? | 6/14/2017 | 6/15/2017
BSI | ? | 6/27/2017 | 6/28/2017
SC | ? | 6/12/2017 | 6/13/2017
BSPR/Bancorp/SFS (TBD) | 6/22/2017 | 6/29/2017 | 6/30/2017
SIS | ? | 7/18/2017 | 7/18/2017
SSLLC | ? | ? | ?
SAM (TBD) | ? | ? | ?
Group (TBD) | RAS Team date | Pre-review CRO date | ERC date
F. Committee and Board Meeting Dates
“?” to be filled in